## Sheet1
Days | Task Name | Expected Timeline | Work Experience | Remark
1 | Static website hosting | 2 days | Understand the concept and collect the Resources
2 | Static website hosting | 2 days | Prepare the documentation
3 | Severless image with lambda | 4 days | Research about everything related to this project
4 | Severless image with lambda | 4 days | After collecting the information, try to start the project | json Code Error
5 | Severless image with lambda | 4 days | Finally completed in whole Day after troubleshooting
6 | Integerated Grafana with Linux | 3 days | Collect the Resources and learn everything about grafana | Difficult to understand
7 | Integerated Grafana with Linux | 3 days | Unable to make it because of errors | some command error
8 | Integerated Grafana with Linux | 3 days | Finally able to make the project with basic understanding